Friends of Bude Park

Minutes of the Meeting held on Tuesday 26th July 2011

1. Minutes & Matters Arising

Cllr Brown had spoken to Ken Blacker regarding a joint project with a walking theme and suggested that the group applies to the local PCT for a grant.

a) JF to arrange a partnership meeting with Ken Blacker (walking group), Susie Moulson (Friends of Fordyke Green), Bodmin Church, Allotment Group, Wardens, Healthy Hearts, Chris Craven (North Carr Area Team) and any other interested party, with the aim of looking at ideas for projects with a positive health aspect that would fit the criteria for grant funding from the PCT & the British Heart Foundation.

Proposed date: Thursday 22nd September 2011 7 – 9pm St Andrews Community Centre

b) Flyers to promote the Community Sport & Fitness Day had been handed out today from the POD based as ASDA Kingswood.

2.  Community Sport & Fitness Event (Recap/Update)

RM has arranged for an Ice Cream vendor (Mr Lister tel 077720195) to attend: a discussion took place around other food outlets: agreed that no other food vendor was necessary due to the short duration of the event.

Tap Water will be available free of charge RM to arrange and buy 500 beakers: cost to be taken from £10 ASDA voucher donated by ASDA. CC to print signage

JF Sports Development is happy with arrangements; providing a rolling programme of events to including golf, football etc: each event will have its own designated coach.  A system of tick cards to be used to record participation: cards to be entered into a raffle at the end of the day prize signed Hull FC shirt and match tickets.

JF Spots & Stripes (Cadburys) attending to run traditional activities to promote competition: Sponsors of Treats for the 2012 Olympics

JF Table Tennis: British Table Tennis Association to coach.  Adizone: iheath to coach

Bouncy Castles & Climbing Wall booked.

JF to collect, from Volcom, 2 marquees, 4 tables and 10 chairs on day of event RM to contact Volcom to amend order: Marquees to be used for St Johns, Groundwork and Friends, CC to bring publicity boards from BeSPoKe. An extra marquee will be available from the Rangers and could be used for cover in the event of rain or sun.

PA system: closest power supply would be from hut JF to look at barriers/cover for leads

JF collecting stickers from supplier on Thursday (for use on banners); RM to display as soon as possible.

JF to let RM have balance of funds available to allow purchase of kid’s trikes:  to be used on the day JF to ask CC if rangers could mark out a trail.

JF to speak to CC re publicity in the Hull Daily Mail: via press office.

JF has a site plan and will be on site early to organise: Friends to be on site approx 12pm

Evaluation Meeting

A meeting to evaluate the day to be held August 16th at 1.30pm (RM house)

Date of next meeting: Tuesday 25th October 2011 1pm – 3pm St Andrews Community Centre